## 3A
DOST Form No. 3A
SEMI-ANNUAL PROGRESS REPORT
for the Period: Yr 2015 Semi_______ (from January to March)
(To be submitted by the researcher quarterly for project with 1 year duration while semi-annually for multi-year project )
(1) PROGRAM TITLE | :
(2) PROJECT TITLE/DURATION | : Deployment of Early Warning Systems in Disaste-prone Areas (DEWS)
(3) COORDINATOR/LEADER | : MIRASOL G. DOMINGO |  | (4) AGENCY:
(5) COOPERATING AGENCIES | :
TARGET ACTIVITIES FOR |  | (8) PERCENTAGE ACCOMPLISHMENT |  | (9) PROJECT
THE PERIOD | (7) ACTUAL ACCOMPLISHMENT | FOR THE | CUMMULATIVE | EXPENDITURES | (10) REMARKS
(RELATE TO FORM 2B-1) |  | PERIOD | (FROM START) | FOR THE PERIOD
Preventive Maintenance, Troubleshooting and Reporting | Conducted Preventive Maintenance, and Troubleshooting on the following sites: Brgy. Sto. Niño, Talaingod, Davao del Norte; Brgy. Cabasagan, Boston, Davao Oriental; PDRRM Office, Tagum City, Davao del Norte; Igacos, Samal, Davao del Norte; MARAGUSAN POBLACION, Compostela Valley; BRGY. ANDAP, Compostela Valley; BRGY. PANAG, Compostela Valley; BRGY. SAN ROQUE, Compostela Valley; MANGAYON ELEMENTARY SCHOOL, Compostela Valley; KALAW BRIDGE, Compostela Valley; ULIP BRIDGE, Compostela Valley; OLAYCON BRIDGE, Compostela Valley; BABAG BRIDGE, Compostela Valley; BRGY. POBLACION COMPOSTELA, Compostela Valley; MONTEVISTA POBLACION, Compostela Valley; MALINAWON, Compostela Valley; Prepared monitoring reports on weather sensors status. | 28.57% | 7% | 102049.96
Quarterly Meeting | Attended 1st Quarter DEWS Meeting in ASTI Quezon City
Trainings | Attended ARG Calibration Training in PAGASA Quezon City
I CERTIFY, ON MY HONOR, TO THE CORRECTNESS OF THE ABOVE INFORMATION.
| Coordinator/Leader |  | Attested:
_____________________________________________
| Date |  |  | Agency Head or Authorized Representative
Rev 1 / 06/26/08

## 4
DOST Form No. 4
SEMI-ANNUAL/ANNUAL FINANCIAL REPORT
(Should include DOST Form No. 7 for annual financial report and Form No. 8 both for quartely and annual financial report)
(To be submitted by accountant and researcher within one month after due date)
(1) Title | [6 empty] | (2) Coordinator/Leader/Gender |  |  | Source of Fund
Program:
Project: | Deployment of Early Warning Systems in Disaste-prone Areas (DEWS) | [5 empty] | MIRASOL G. DOMINGO/Female |  |  | DOST/PCIEERD
(3) Period Covered |  | (4) Date when fund for quarter was |  |  |  |  | (5) Implementing Agency/
February-March 2015 |  | received by implementing Agency |  |  |  |  | Research & Development Station
|  | (7) Total | (8) | Releases |  | (9) | Disbursements |  | (10) | (10) | (11) | (12)
|  | Approved | ___Year of Implementation |  |  | ___Year of Implementation |  |  | Accounts | Total | Unreleased | Unexpended
(6) Particulars |  | Budget for the | Total | Total | Total | Total | Total | Total | Payable | Expenditures | Budget | Budget
|  | Year | Previous | This | To Date | Previous | This | To Date | To Date | To Date | To Date | To Date
|  |  | Quarter | Quarter |  | Quarter | Quarter
I. Personal Services
Salaries/Wages
One (1) SRS I @ P 25,723/month x 6 mos. |  | 63547.83 | 0 | 63547.83 | 63547.83 | 0 | 58734.05 | 58734.05 |  | 58734.05 |  | 4813.78
Honoraria
One (1) Project Staff L3 @P7,500/mo. X 12 mos. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
One (1) Project Staff L2 @P6,000/mo. X 12 mos. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
One (1) Project Support Staff L2 @P1,500/qtr. X 2 qtr. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
Sub-total for PS |  | 63547.83 | 0 | 63547.83 | 63547.83 | 0 | 58734.05 | 58734.05 |  | 58734.05 | 0 | 4813.78
II. MOOE
Travelling Expenses (Local) |  | 20320.05 | 0 | 20320.05 | 20320.05 | 0 | 31694 | 31694 |  | 31694 |  | -11373.95
Communication Expenses (mobile) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
Supplies and Materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
Office Supplies |  | 3023.95 | 0 | 3023.95 | 3023.95 | 0 | 0 | 0 |  | 0 |  | 3023.95
Fuel |  | 0 | 0 | 0 | 0 | 0 | 3771.91 | 3771.91 |  | 3771.91 |  | -3771.91
Rent Expenses |  | 11000 | 0 | 11000 | 11000 | 0 | 7850 | 7850 |  | 7850 |  | 3150
Representation Expenses |  | 11995 | 0 | 11995 | 11995 | 0 | 0 | 0 |  | 0 |  | 11995
Other Professional Services (production of ….) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
Sub-total for MOOE |  | 46339 | 0 | 46339 | 46339 | 0 | 43315.91 | 43315.91 |  | 43315.91 | 0 | 3023.09
III. Equipment Outlay
One (1) unit laptop |  | 6005 |  | 6005
Sub-Total |  | 6005 | 0 | 6005 | 6005 | 0 | 0 | 0 |  | 0 | 0 | 6005
T O T A L |  | 115891.83 | 0 | 115891.83 | 115891.83 | 0 | 102049.96 | 102049.96 |  | 102049.96 | 0 | 13841.87
CERTIFIED CORRECT: |  |  | VERIFIED: (For NGOs or Privately owned institutions) |  |  |  | NOTED: |  |  | APPROVED:
Chief Accountant |  |  | Auditor |  |  | Research Coordinator/Leader |  |  |  | Agency Head or
| PTR/License No.__ |  | PTR/License No.__ | [6 empty] | Authorized Representative
Rev 1 / 06/26/08